## Sheet1
|  |  | 2008-09-22 | B+H | M+Sherwin | P+Stu
|  |  | 2008-09-29 | H+Stu | M+Sherwin
|  |  | 2008-10-13 | Sori+Stu | M+Eric
|  |  | 2008-10-20 | Sori+Sher | M+Hugs | Eric+Stu
|  |  | 2008-10-27 | Sher + Eric | Hugs+Sori | M+Stu
| Started W/out peter | Effort | Priority
|  |  | 0-10 | Team 1 | Team 2 | Team 3
1. Firestarter rewrite |  | 16
a. Reverse Engineering from Database. Pluggable such that can extend to any database easily. Need to be able |  | 4
b. Model Business Objects. I.e. Build easy to use – user interfaces using Habanero Business Objects. Use a normal database to start. | Y | 8 | 9 | 4
c. Track what has been generated and what has been changed s.t. can control generation i.e. if the class has been generated then don’t regenerate also need to be able to do this for relationships or properties. I.e. if you override the relationship behaviour then want to be able to not regenerate. | Y | 1 | 6
d. Generate to code. Must be written such that can plug other templates into generator. | Y | 1 | 8
e. Save the Business Model to XML instead of a database | Y | 2 | 9 dep b
2. Reorganise Habanero.Base |  | 1 | 1
3. Check For Duplicates in same transaction as commit | Y | 1 | 4
4. Lookups Define philosophy and rework |  | 4 | 6
5. Relationships define philosophy and implement |  | 12 | 10
6. Generate Tests for BO’s | Y | 2 | 6.1
7. Generate Forms
a. Simple CRUD Grid - Read only Grid, Editable Grid | Y | 2 | 10 |  | 2
b. CRUD Editor Form – Selector and BO Editor. | Y | 2 | 10 |  | 2
c. Parent Child Form (Master – Child). Select master (possibly edit) get list of children select child edit. E.g. Customer – Orders. | Y | 4 | 7
d. Generate tests | Y | 2 | 10 |  | **
8. Generate Database Structure and manage versions of application with different databases. (dep 1)
9. Refactor Panel Factory | Y | 4 | 8 |  |  | 4
10. FindBy |  |  | 7
a. Create classes
b. Generate
c. Investigate LINQ
11. Gen/Dynamically define search criteria in ClassDefs for a Grid (dep 1) | Y
12. Develop a set of UI test utils | Y | ongoing
13. Study WPF, Silverlight etc |  | 12 | 3
14. Define Triggers in ClassDefs (dep on 9) |  |  | 0.5
15. Mutable Composite primary key for Readonly and editable grid. Sample app using Northwind. | Y | 1 | 8 |  |  | 1
16. Globalisation of all error messages. | Y | 3 | 5
17. Email error messages | Y | 1 | 9 |  |  | 1 | nearly done - just need form for user to enter further information
18. Have option to do an SDI interface. |  | 1 | 2
19. Allow multiple class defs for a project. |  |  | 1
20. Allow bulk deleting of rows in a grid. | Y | 1 | 6
21. Create functionality to allow the object and collection to dump its state. See Serialisable | Y | 2 | Dep 25
22. Create Display objects i.e. object that can load based on any defined SQL load (allow summing, counting and other aggregate functions) and cannot be edited. This will replace loading these through a view. |  | 3 | 3
23. Allow the plugging in of any Database mapping logic for both reading and writing. |  | 4 | 2
24. Create N-Tier Demo. |  | 2 | Dep 25
25. Serialisable Business objects and collections. | Y | 2 | 8 |  |  | 2
26. Compact framework investigation |  | R&D
27. Reports (dep 22) |  | 12 | Dep 22
28. Support generation of VB.Net code. | Y | 1 | 7 |  |  | 1
29. Collapsible Panel |  | 1 | 1